## Group C (baseline-Post_INF)
Project CFR02: (AIM-2) SIVmac251 infected macaques + BLZ945 | [6 empty] | Group C/E
(n=6) per group
Revised: 10/05/2023-la | [6 empty] | mmu #: 44044; 44300; 44321; 45514; 45706; 46261
PID= Post Infection Day
Time points | [7 empty] | Blood volumes | [5 empty] | Notes
| PID | DATE | Post-ART | GROUP E | WO | Injections | Procedures | EDTA (Kuroda) | CBC | CHEM20 | Chem12 (PP3) | Sera tube | Blood vol Totals
| -55 | 2022-02-24 |  | x | 5538 v2 | (Chris Royer) | AEROSOL: Dextran | 10 | 1 | 1 | 0 | 0
|  | 2022-02-24 |  | x |  |  | fasted PE (BCS)
| -51 | 2022-02-28 |  | x | 5593 v3 | IV and IT: Dextran | CSF 1-2 mL | 5 | 1 | 0 | 0 | 0
| -41 | 2022-03-10 |  | x | 5843 | (Chris Royer) | BAL 2x20 mL (RIGHT) | 0 | 0 | 0 | 0 | 0
D0 | -37 | 2022-03-14 |  | x | 5869 | IV: BrdU |  | 0 | 0 | 0 | 0 | 0
D1-T24 | -36 | 2022-03-15 |  | x | 5884v2 |  |  | 10 | 1 | 1 | 0 | 0
D4 | -33 | 2022-03-18 |  | x | 5937v2 | Bx | LN (peripheral) | 10 | 1 | 0 | 0 | 0
Fat (SubQ)
D7 | -30 | 2022-03-21 |  | x | 5961 |  |  | 5 | 0 | 0 | 0 | 0
D15 | -23 | 2022-03-28 |  | x | 6051v2 |  |  | 5 | 0 | 0 | 0 | 0 |  | (except 45514)
| -16 | 2022-04-04
| -9 | 2022-04-11 |  | x | 6390 |  | CSF 1-2 mL
| 0 | 2022-04-20 |  | x | 6514 | IV: SIVmac251 | fasted PE (BCS) | 10 | 1 | 1 | 0 | 0
| 6 | 2022-04-26 |  | x | 6601v2 | SQ: CD8 depletion |  | 2 | 0 | 0 | 0 | 0
D0 | 8 | 2022-04-28 |  | x | 6643 | IV: CD8 depletion |  | 0 | 0 | 0 | 0 | 0
|  | 2022-04-28 |  |  |  | IV: BrdU
D1-T24 | 9 | 2022-04-29 |  | x | 6661 |  |  | 10 | 1 | 0 | 1 | 0
D4 | 12 | 2022-05-02 |  | x | 1012 | IV: CD8 depletion | CSF 1-2 mL | 10 | 1 | 0 | 0 | 0 |  | (except 45706)
D7 | 15 | 2022-05-05 |  | x | 1199 |  |  | 10 | 1 | 0 | 0 | 0 |  | (CBC only 45706)
D14 | 22 | 2022-05-12 |  | x | 1298 |  | CSF 1-2 mL | 5 | 1 | 0 | 0 | 0
D0 | 35 | 2022-05-25 |  | x | 1491 | IV: BrdU
D1-T24 | 36 | 2022-05-26 | 0 | x | 1517v2 | ART Start |  | 5 | 1 | 1 | 0 | 0 | Administer ART, POST-blood collection |  | ART
D0 | 68 | 2022-06-27 | 32 |  | 2021 | IV: BrdU |  | 0 | 0 | 0 | 0 | 0
D1-T24 | 69 | 2022-06-28 | 33 |  | 2024 |  |  | 10 | 1 | 1 | 0 | 0
D0 | 141 | 2022-09-08 | 105 |  | 3209 | IV: BrdU |  | 0 | 0 | 0 | 0 | 0
D1-T24 | 142 | 2022-09-09 | 106 |  | 3217 |  |  | 10 | 1 | 1 | 0 | 0
D4 | 145 | 2022-09-12 | 109 |  | 3228 | Bx | LN (peripheral) with FAT (SubQ) | 15 | 1 | 0 | 0 | 0
BM (1mL)
| 174 | 2022-10-11 | 138 |  | 3643v2 | (Chris Royer) | BAL 2x20 mL (LEFT) | 0 | 1 | 0 | 0 | 0
14day post-BAL | 188 | 2022-10-25 | 152 |  | 3786 | Dextran (Aero, IV) |  | 10 | 1 | 1 | 0 | 5
[6 empty] | DEX-IT (RO) | CSF 1-2 mL
Notatation for the order of the Dextran administration.
[7 empty] | 1.- | IT/IC (to ensure the deepest sedation)
[7 empty] | 2.- | Aerosol
[7 empty] | 3.- | IV (reduce manipulation of injection site post-procedure)
------> > xxx days post-Dextran; GROUP E Begin BLZ945 for 4 weeks; EDU treatment; REPOPULATION; then Nx < < -------------
NO BLZ for Group C
Formulas:
Post-ART = DAYS([DATE],C28)

## CFR02-NEW Group-C (TRX+Nx)
Project CFR02: (AIM-2) SIVmac251 infected macaques + BLZ945 | [7 empty] | BLZ945 TRX: Early +Repopulation
SIV infected: |  | 2022-04-20 |  |  | ART initiated= |  | 2022-05-26 | Group C: ONLY n=2 (44300;46261)
Revised: 10/05/2023-la | [6 empty] | *NOTE: --> AFTER 10/25/2022 Dextran dosing; modified from original Group E (n=6)
New Group C (moved 44044, 44321, 45514, 45706 to new Group E)
------> > 34 days post-Dextran; Begin EDU in parallel with Group E; then Nx < < -------------
Begin 7-day drinking solution with EDU to time with 2 days prior to end of Group E BLZ495 treatment
Time points | [8 empty] | Blood volumes
| PID | DATE | post-ART (days) | WO | Group C (n=2) |  | Injections | Procedures | EDTA (Kuroda) | CBC | Chem 20 | Chem12 (PP3) | Sera tube
[5 empty] | 46261 | 44300 |  |  | EDTA (Kuroda) | CBC | Chem 20 | Chem12 (PP3) | Sera tube | ART
| 229 | 2022-12-05 | 193 | 4428 | x | x | Begin EDU drinking solution (in parallel with Group E)
D0 | 237 | 2022-12-13 | 201 | 4510 | x | x | IV: BrdU |  | 0 | 0 | 0 | 0 | 0
D1-T24 | 238 | 2022-12-14 | 202 | 4538 | x | x |  |  | 10 | 1 | 1 | 0 | 0
D0 | 278 | 2023-01-23 | 242 | 4975 | (46261) | -- | IV: BrdU |  | 0 | 0 | 0 | 0 | 0
D1-T24 | 279 | 2023-01-24 | 243 | 4985 | (46261) | -- |  |  | 10 | 1 | 1 | 0 | 0
D0 | 282 | 2023-01-27 | 246 | 5032v2 | (46261) | -- | Nx#1 (46261) |  | 0 | 0 | 0 | 0 | 0
D1-T24 | 299 | 2023-02-13 | 263 | 5297 | -- | (44300) | IV: BrdU |  | 10 | 1 | 1 | 0 | 0
D4 | 300 | 2023-02-14 | 264 | 5322v2 | -- | (44300) |  |  | 50 | 1 | 1 | 0 | 10
D4 | 303 | 2023-02-17 | 267 | 5378v2 | -- | (44300) | Nx#2 (44300) |  | 50 | 1 | 1 | 0 | 10
[9 empty] | 0 | 0 | 0 | 0 | 0
To Nx
Formulas:
post-ART (days) = DAYS([DATE],H2)